## Case1_Detailed_MTC
[8 empty] | Risk Category | Risk Type |  | Strategy | Impact
[9 empty] | Volume Loss or Shift |  | Avoid | Risk Adjusted CC
[8 empty] | Customer/Supplier | Product Excess Cost |  | Reduce/Mitigate | Add. Cost
[8 empty] | Market/Political | Operative Excess Cost |  | Transfer | Management
[8 empty] | Product Release | Penalties |  | Contingent Plan | Committed Cost
[8 empty] | Project Logistics | Price Erosion |  | Accept |  |  | 100
[8 empty] | Project Execution | AR Delay |  | Exploit
[8 empty] | Contractual/Legal | Bond |  | Share
[8 empty] | Financial | Warranty |  | Enhance
[8 empty] | Others | Termination | Remedy | [15 empty] | 20 |  | #REF!
[9 empty] | Inflation | Pro-active | [15 empty] | 22 |  | #REF!
[9 empty] | Currency Hedging | Reactive | [15 empty] | 30 |  | #REF!
[10 empty] | Pro + Pre | [15 empty] | 23 |  | #REF!
[25 empty] | ACTION |  | Threat after Control |  |  |  | Threat after Control + Cont.
Risk ID | Project Name | Raised By | Risk Owner | Risk Event (What might happen?) | Root Cause (Reason) | Consequences/Impact (Result) | Proximity (Materialized Date) | Risk Category | Risk Type | Remedy | Response Strategy | Response Impact | Response Action Summary | OPT./Min. Impact | TYPICAL Impact | PESS./Max. Impact | PERT Mean | Triangle Mean | Beta Model Mean | Estimated Prob. Of Occurrence | Mean Impact (PERT/Triang/Beta) | likelihood of this Impact | Estimated Impact | Initial EV | Control Prob. | Control Impact | Residual EV | Cost of Control (CoC) | Contingency Reserve | Management Reserve | Residual NEV | Risk Cost | Risk Budget | Residual Proximity Date | Secondary Risk (If any) | Risk Status (Active/Closed) | Risk Actionee
[17 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0% | 0% | 0 |  |  |  | 0 | 0 | 0
1 | CUST_A | Yasser Soliman | Yasser Soliman | Project Shutdown | Customer Own Interest | Sales volume Drop by 50%, GM drop by 20% |  | Contractural/Legal | Termination |  |  | Management | Supplier/Sub-contractor Credit Rating |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0% | 0% | 0 |  |  |  | 0 | 0 | 0 |  |  |  | XXX
[5 empty] | Contract breach - wrong plan | Shutdown Cost - dismissal of Employee | [5 empty] | Add. Cost | Highly Skilled PM (Monitor, Control, PIP) |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0% | 0% | 0 |  |  |  | 0 | 0 | 0
[5 empty] | Contract breach - Lack of SoW | Shutdown Cost - dismissal of Redeployment of Asset | [5 empty] | Management | Well Defined Triggers of Breaching Clauses |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0% | 0% | 0 |  |  |  | 0 | 0 | 0
[5 empty] | Contract breach - Lack of resources | Uncovered Sunk Cost | [5 empty] | Management | Well Defined Responsibility Matrix (RACI) - SoR |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0% | 0% | 0 |  |  |  | 0 | 0 | 0
[6 empty] | Loss of Anticipated Profit | [5 empty] | Management | Avoid penalty/termination in Contract Clauses |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0% | 0% | 0 |  |  |  | 0 | 0 | 0
[6 empty] | Brand/Reputation Damage | [5 empty] | Management | Bundled Offers |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0% | 0% | 0 |  |  |  | 0 | 0 | 0
[12 empty] | Management | Back to Back agreement with 3rd party |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0% | 0% | 0 |  |  |  | 0 | 0 | 0
[12 empty] | Management | Lock_In period |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0% | 0% | 0 |  |  |  | 0 | 0 | 0
[12 empty] | Management | Termination Fee |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0% | 0% | 0 |  |  |  | 0 | 0 | 0
[12 empty] | Management | Notice Period |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0% | 0% | 0 |  |  |  | 0 | 0 | 0
[12 empty] | Management | Limit Penalty amount in contract clauses |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0% | 0% | 0 |  |  |  | 0 | 0 | 0
[12 empty] | Management | Secure Customer Outstanding payment after termination | 62000 | 86000 | 136000 | 90333.3333 | 94666.6667 | 90810 | 40% | 90333.3333 | 75% | 98652.0403 | 39460.8161 | 50% | 50% | 9865.204 |  | 7000 | 1000 | 1865.204 | 7000 | 8000
[12 empty] | Committed Cost | Contingent Plan | 62000 | 86000 | 136000 | 90333.3333 | 94666.6667 | 90810 | 40% | 94666.6667 | 75% | 105062.4675 | 42024.987 | 50% | 60% | 8404.9974 | 10000 | 2000 | 1000 | 5404.9974 | 12000 | 13000
[14 empty] | 15000 | 25000 | 28000 | 23833.3333 | 22666.6667 | 23705 | 40% | 23833.3333 | 80% | 25656.846 | 10262.7384 | 40% | 30% | 4310.3501 | 0 |  | 4000 | 310.3501 | 0 | 4000
[24 empty] | Initial EV |  |  | Residual EV | Cost of Control (CoC) | Contingency Reserve | Management Reserve | Residual NEV | Risk Cost | Risk Budget
[24 empty] | 91748.5415 |  |  | 22580.5516 | 10000 | 9000 | 6000 | 7580.5516 | 19000 | 25000
Total Price calculation
[14 empty] | Before Mitigation | After Mitigation
[14 empty] | Total | Total
[12 empty] | Initial Solution Cost |  | 91999 | 91999
[12 empty] | Initial Sales Price |  | 131500 | 131500
[12 empty] | Risk - Initial EV |  | 91748.5415 | 91748.5415
[12 empty] | Risk - Residual NEV |  | 91748.5415 | 7580.5516
[12 empty] | Risk Cost (Excluding Contract Penalties) |  |  | 19000
[12 empty] | Sales Price (Initial Sales + Risk Cost) |  | 131500 | 150500
[12 empty] | Cost Baseline (Sol. Cost+Risk Cost) |  | 91999 | 110999
[12 empty] | GM% |  | 30.04% | 26.25%
Penalty Calculation
[14 empty] | Total | Total
[12 empty] | Cost Baseline (Sol. Cost+Risk Cost) |  | 91999 | 110999
[12 empty] | Sales Price |  | 131500 | 150500
[12 empty] | Penalty % | 0%
[12 empty] | Penalty Probability | 0%
[12 empty] | Penalty EV = Penalty * Probability |  | 0 | 0
Finanl Price = Sales Price + Penalties
[12 empty] | Final Sales Price (Init. Sales + Risk + Penalties) |  | 131500 | 150500
[12 empty] | Total Cost (Sol. Cost+Risk Cost) |  | 91999 | 110999
[12 empty] | Penalties |  | 0 | 0
[12 empty] | Total Cost (Sol. Cost+Risk Cost+ Penalty) |  | 91999 | 110999
[12 empty] | GM (Risk Cost + Penalty) |  | 30.04% | 26.25%
[12 empty] | GP |  | 39501 | 39501
[29 empty] | Impact |  |  | Probability
[30 empty] | 0 |  |  | 0.5%
[29 empty] | 1 | 1976 |  | 1 | 21%
[29 empty] | 2 | 5926 |  | 2 | 51%
[29 empty] | 3 | 15801 |  | 3 | 99%
[29 empty] | 4 | 27651
[29 empty] | 5 | 39501
[28 empty] | Cost of Risk Control = | 0.8 | Initial Residual Risk
[28 empty] | Expected Value Status |  | Severity Level |  | GP Loss % | New GM%
[28 empty] | 1 | 1 | Negligible | < 1,976 | 5% | 28.54%
[28 empty] | 5925 | 2 | Minor | 1,976 - 5,926 | 15% | 25.53%
[28 empty] | 15800 | 3 | Serious | > 5,926 - 15,801 | 40% | 18.02%
[28 empty] | 27650 | 4 | Major | > 15,801 - 27,651 | 70% | 9.011%
[28 empty] | 39500 | 5 | Severe | > 27,651 - 39,501 | 100% | 0%
PROBABILITY
[30 empty] | 1 | 2 | 3
[30 empty] | Low | Medium | High
[30 empty] | < 0.21 | 0.21 - 0.51 | > 0.51 - 0.99

## Input_Data
1 | 2 | 3 |  | 1 | 2 | 3 | 4 | 5
Low | Medium | High |  | Negligible | Minor | Serious | Major | Severe
< 0.21 | 0.21 - 0.51 | > 0.51 - 0.99 |  | < 1,976 | 1,976 - 5,926 | > 5,926 - 15,801 | > 15,801 - 27,651 | > 27,651 - 39,501
Insert Data in Yellow Cells |  |  |  | Cost = | 91999 |  |  | Initial Residual Risk
|  |  |  | Price = | 131500 |  | Cost of Risk Control = | 80%
|  |  |  | Initial GM = | 30.04%
|  |  |  | GP = | 39501
Probabiliy | % |  |  | Impact | New GM | % Loss from Initial GP | GP Loss Value < | GP Left
Low | 21% |  | 0.28971 | 1- Negligible | 28.54% | 5% | 1976 | 37525
Medium | 51% |  |  | 2- Minor | 25.53% | 15% | 5926 | 33575
High | 99% |  |  | 3- Serious | 18.02% | 40% | 15801 | 23700
|  |  |  | 4- Major | 9.011% | 70% | 27651 | 11850
|  |  |  | 5- Sever | 0% | 100% | 39501 | 0

## Expected Impact (hidden)
PERT Mean | PERT Std | Triangle Mean | Triangle Std | Beta Model Mean | Beta Std | Selected Mean | Selected Std | Probability | Expected Impact
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
90333.3333 | 12333.3333 | 94666.6667 | 15412.8374 | 90810 | 23365.0144 | 90333.3333 | 12333.3333 | 75% | 98652.0403
90333.3333 | 12333.3333 | 94666.6667 | 15412.8374 | 90810 | 23365.0144 | 94666.6667 | 15412.8374 | 75% | 105062.4675
23833.3333 | 2166.6667 | 22666.6667 | 2778.8887 | 23705 | 4299.7645 | 23833.3333 | 2166.6667 | 80% | 25656.846